## Sheet1
Sprint Retro 2
What went well | What went bad | What can be improved (actions)
Acted on improvements | Little rushed bit of time and stressed | Code review in morning (along with demo)
Login system now works (in theory) | Breakout sessions | Be chill, its fine, we got this, go team
Most of database interaction done | Big project that we have to fit in 3 days | TDD where you can! (but running out time)
Front end basis now set and needs linking up | TDD went slightly out of the window towards the end | Code structure in places can be improved
Hashing (SHA-256) | Tom and Rohan had lots of problems with running
Teamwork | No time for code reviews
Learnt new skills | No time for presentation prepare
Pairing pairs | Time
Constant communication is good
Doing some work after work